## Sprint-1
|  |  |  | Week #1 (64 hrs / week) | [6 empty] | Week #2 (64 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13
|  |  |  | 128 | 118 | 108 | 98 | 88 | 78 | 68 | 58 | 48 | 38 | 28 | 18 | 8 | 0 | Ideal Burndown
|  |  | 128 | 128 | 124 | 120 | 116 | 112 | 107 | 106 | 94 | 80 | 66 | 54 | 40 | 26 | 12 | Remaining Hrs (Total)
Project-wise tasks | Create initial class diagram | Rajat | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 3
| Setup Github repo and making initial commits | Utkarsh | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 6 | 5 | 4 | 3 | 2 | 1 | 0
| Bug fix: booking and amenity restful CRUD | Junjie | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Enable user to use the booking application | Start with IOS app setup as frontend | Sahib | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 0
| Start with Srpintboot setup as backend | Junjie | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3
| Start with MongoDB setup as database | Utkarsh | 26 | 26 | 24 | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 8 | 6 | 4 | 3
Enable user to see the login/signup page | Implement frontend login/sign-up page | Sahib | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 3
Enable user to see the home page | Implement frontend home page | Sahib | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 10 | 8 | 6 | 4 | 2 | 0 | 0
Enable user to make a simple booking | Implement backend RESTful booking services | Junjie | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Build booking infrastructure | Junjie | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enable user to choose amenity during booking | Implement backend RESTful amenity services | Junjie | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 1 | 0
| Build amenity infrastructure | Junjie | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 1 | 0
Working Time
Team Member: | In a week: | In a sprint:
Junjie | 16 hours / Week | 32 hours / Spint
Sahib | 16 hours / Week | 32 hours /Spint
Rajat | 16 hours / Week | 32 hours / Spint
Utkarsh | 16 hours / Week | 32 hours / Spint
Total | 64 hours / Week | 128 hours / Sprint

## Sprint-2
|  |  |  | Week #1 (64 hrs / week) | [6 empty] | Week #2 (64 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27
|  |  |  | 128 | 118 | 108 | 98 | 88 | 78 | 68 | 58 | 48 | 38 | 28 | 18 | 8 | 0 | Ideal Burndown
|  |  | 128 | 128 | 112 | 106 | 100 | 94 | 87 | 82 | 76 | 66 | 54 | 41 | 29 | 20 | 12 | Remaining Hrs (Total)
Project-wise tasks | Setup Slack, Jira, produt design, documentation | Sahib | 18 | 18 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 0
| Refine booking process, fix bugs | Junjie | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3
Enable user to login and signup | Implement backend RESTful login/signup services | Utkarsh | 16 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 3
| Build login/signup infrastructure | Utkarsh | 16 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0
Enable user to choose a hotel during booking | Implement backend RESTful hotel services | Junjie | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Build hotel infrastructure | Junjie | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enable user to choose a room during booking | Implement backend RESTful room services | Junjie | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 1 | 0
| Build room infrastructure | Junjie | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 1 | 0
Enable user to have its bill after booking | Implement backend RESTful bill services | Rajat | 16 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 9 | 8 | 6 | 5 | 4 | 3
| Build bill infrastructure | Rajat | 16 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 6 | 4 | 2 | 0 | 0
Enbale user to see its booking info after booking | Implement frontend my booking page | Sahib | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 10 | 8 | 6 | 4 | 3 | 3
Working Time
Team Member: | In a week: | In a sprint:
Junjie | 16 hours / Week | 32 hours / Spint
Sahib | 16 hours / Week | 32 hours /Spint
Rajat | 16 hours / Week | 32 hours / Spint
Utkarsh | 16 hours / Week | 32 hours / Spint
Total | 64 hours / Week | 128 hours / Sprint

## Sprint-3
|  |  |  | Week #1 (64 hrs / week) | [6 empty] | Week #2 (64 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10
|  |  |  | 128 | 118 | 108 | 98 | 88 | 78 | 68 | 58 | 48 | 38 | 28 | 18 | 8 | 0 | Ideal Burndown
|  |  | 128 | 128 | 126 | 117 | 108 | 101 | 93 | 87 | 84 | 78 | 65 | 54 | 36 | 26 | 12 | Remaining Hrs (Total)
Project-wise tasks | Refine booking page UI | Sahib | 18 | 18 | 18 | 15 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 0
| Postman API Documentation | Junjie | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 2 | 0
| Refine booking process, fix bugs | Junjie | 12 | 12 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 3 | 2 | 0
| Sync with frontend on home page | Junjie | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3
| Sync with frontend on login/signup page | Utkarsh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 2 | 0
Enable user to know the real time pricing for hotel | Implement backend RESTful dynamic pricing services | Utkarsh | 12 | 12 | 12 | 12 | 12 | 12 | 11 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 3
| Add on dynamic pricing infrastructure to hotel | Utkarsh | 12 | 12 | 12 | 12 | 12 | 12 | 11 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0
Enable user to make a payment to the booking | Implement backend RESTful payment services | Rajat | 16 | 16 | 16 | 14 | 12 | 10 | 8 | 6 | 6 | 6 | 5 | 5 | 4 | 3 | 3
| Build payment infrastructure | Rajat | 16 | 16 | 16 | 14 | 12 | 10 | 8 | 6 | 6 | 6 | 5 | 5 | 2 | 2 | 0
Enbale user to see the hotel detail | Implement frontend hotel detail page | Sahib | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 10 | 8 | 6 | 4 | 3 | 3
Working Time
Team Member: | In a week: | In a sprint:
Junjie | 16 hours / Week | 32 hours / Spint
Sahib | 16 hours / Week | 32 hours /Spint
Rajat | 16 hours / Week | 32 hours / Spint
Utkarsh | 16 hours / Week | 32 hours / Spint
Total | 64 hours / Week | 128 hours / Sprint

## Sprint-4
|  |  |  | Week #1 (64 hrs / week) | [6 empty] | Week #2 (64 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24
|  |  |  | 128 | 118 | 108 | 98 | 88 | 78 | 68 | 58 | 48 | 38 | 28 | 18 | 8 | 0 | Ideal Burndown
|  |  | 128 | 128 | 126 | 123 | 120 | 113 | 106 | 99 | 86 | 78 | 47 | 40 | 32 | 16 | 12 | Remaining Hrs (Total)
Project-wise tasks | Refine hotel detail page UI | Sahib | 18 | 18 | 18 | 15 | 12 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 2 | 0
| Refine booking and bill entity | Rajat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 2 | 0
| Sync with frontend on hotel detail page, add image and url | Junjie | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0
| Fix holiday price and date | Utkarsh | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 5 | 4 | 2 | 0 | 0
Enable user to know why booking has fail | Implement backend RESTful bookimg validating services | Junjie | 12 | 12 | 12 | 12 | 12 | 12 | 11 | 10 | 10 | 9 | 6 | 3 | 3 | 3 | 3
| Add on booking validating to booking process | Junjie | 12 | 12 | 12 | 12 | 12 | 12 | 11 | 10 | 10 | 8 | 5 | 5 | 2 | 0 | 0
Enable user to use the reward point during the payment | Implement backend RESTful reward point services | Rajat | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3
| Add on reward point infrastructure on user | Rajat | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 6 | 6 | 3 | 3 | 3 | 0 | 0
Enbale user to see and use the hotel searching | Implement frontend searching page | Sahib | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 10 | 5 | 5 | 5 | 3 | 3
| Implement backend searching service | Utkarsh | 16 | 16 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 10 | 5 | 5 | 5 | 3 | 3
Working Time
Team Member: | In a week: | In a sprint:
Junjie | 16 hours / Week | 32 hours / Spint
Sahib | 16 hours / Week | 32 hours /Spint
Rajat | 16 hours / Week | 32 hours / Spint
Utkarsh | 16 hours / Week | 32 hours / Spint
Total | 64 hours / Week | 128 hours / Sprint

## Sheet5
|  |  |  | Week #1 (64 hrs / week) | [6 empty] | Week #2 (64 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08
|  |  |  | 128 | 118 | 108 | 98 | 88 | 78 | 68 | 58 | 48 | 38 | 28 | 18 | 8 | 0 | Ideal Burndown
|  |  | 128 | 128 | 108 | 94 | 88 | 79 | 71 | 68 | 60 | 50 | 41 | 41 | 20 | 4 | 0 | Remaining Hrs (Total)
Project-wise tasks | Refine UI for all pages | Sahib | 12 | 12 | 10 | 8 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 3 | 0 | 0
| Add get booking page | Sahib | 12 | 12 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 2 | 1 | 1 | 0
| Sync with payment API and Bill object | Sahib | 8 | 8 | 6 | 5 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0
| Deploy application to AWS | Utkarsh | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0
| Refine dynamic pricing, add new amanities and images | Utkarsh | 16 | 16 | 14 | 12 | 10 | 8 | 6 | 6 | 6 | 5 | 4 | 4 | 2 | 1 | 0
| Add new amanities and images | Utkarsh | 12 | 12 | 10 | 8 | 7 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
| Clean up database and add mock data, fix bugs | Rajat | 10 | 10 | 8 | 6 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 0 | 0
| Implement get booking by user email REST API | Rajat | 16 | 16 | 14 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 2 | 1 | 0
| Refine reponse field of REST API | Rajat | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 3 | 3 | 1 | 0 | 0
| Implement chain of responsibilities design pattern | Junjie | 16 | 16 | 14 | 12 | 10 | 8 | 6 | 6 | 5 | 4 | 3 | 3 | 1 | 0 | 0
| Refactor bill services to support update booking services | Junjie | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 3 | 3 | 1 | 1 | 0
| Refine booking process, fix bugs | Junjie | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 3 | 3 | 1 | 0 | 0
Working Time
Team Member: | In a week: | In a sprint:
Junjie | 16 hours / Week | 32 hours / Spint
Sahib | 16 hours / Week | 32 hours /Spint
Rajat | 16 hours / Week | 32 hours / Spint
Utkarsh | 16 hours / Week | 32 hours / Spint
Total | 64 hours / Week | 128 hours / Sprint